## Sheet1
Task | Detailed task | Note | Start Date | End Date | Responsible / Command / POC (Coordinate)
Django / Git Setup | Django |  | 2022-02-08 | 2022-02-09 | Tejas / Shrutika
| Git -> Push Code |  |  |  | Tejas / Shrutika
Design System Flow | Front End |  | 2022-02-08 | 2022-02-09 | Smriti, Vaibhavi / Shrutika
| ChatBot Behavior |  |  |  | Lawrence, Vaibhavi / Tejas, Shrutika
| Backend Connectivity |  |  |  | Tejas / Shrutika
| DB requirements |  |  |  | Vaibhavi, Smriti / Shrutika
Develop Front End |  | Fill Tasks after designing system flow | 2022-02-09 |  | Smriti, Tejas, Shrutika / Tejas / Shrutika
Create DB | Create DB | Structure DB after designing system flow | 2022-02-09 |  | Smriti / Tejas / Shrutika
| Establish Connectivity with Backend |  |  |  | Smriti / Tejas / Shrutika
Develop Backend | Functions to respond with Front End |  | 2022-02-09 |  | Tejas / Shrutika
Develop ChatBot | Fully functional ChatBot | Fill behaviour after designing system flow | 2022-02-09 |  | Lawrence, Vaibhavi, Shrutika / Lawrence / Shrutika
Connect Front End & Backend | Display data for Front End (except chat) |  |  |  | Tejas / Shrutika
Connect ChatBot & DB | ChatBot -> Get data from DB |  |  |  | Tejas / Lawrence / Shrutika
Connect Front End & ChatBot | User interaction with ChatBot from Front End |  |  |  | Tejas / Lawrence / Shrutika
Testing
Upload on AWS
MVP | 2022-03-02 | A FUNTIONAL PROTOTYPE SHOULD BE PRESENTED TO THE PM WITH AT LEAST 20% OF ALL APPROVED FEATURES AND FUNTIONS RUNNING. A TASK WILL BE CREATE NO THE WEBSITE TO ASSIGN THIS GRADE TO EACH STUDENT MEMBER OF THE TEAM. ALL TEAM MEMBER SHOUlD SUBMIT A LINK TO THE TEAM GITHUB TO HAVE THIS RECORD ON THE SYSTEM AND RECEIVE THE MARK.
MMP | 2022-03-30 | A REAL PRODUCT SHOULD BE PRESENTED TO THE PM WITH AT LEAST 75% OF ALL APPROVED FEATURES AND FUNTIONS RUNNING. A TASK WILL BE CREATE NO THE WEBSITE TO ASSIGN THIS GRADE TO EACH STUDENT MEMBER OF THE TEAM. ALL TEAM MEMBER SHOUlD SUBMIT A LINK TO THE TEAM GITHUB TO HAVE THIS RECORD ON THE SYSTEM AND RECEIVE THE MARK.
Formal Presentation | 2022-04-20 | FORMAL PRESENTATION, PRODUCT APPROVED AND FINAL MARK. A TASK WILL BE CREATE NO THE WEBSITE TO ASSIGN THIS GRADE TO EACH STUDENT MEMBER OF THE TEAM. ALL TEAM MEMBER SHOUlD SUBMIT A LINK TO THE TEAM GITHUB TO HAVE THIS RECORD ON THE SYSTEM AND RECEIVE THE MARK.